## Slide 1: How did you manage your project?
EMEE20002 Management Assessment

## Slide 2: Contents
Project Summary and Charter
Team Structure
Planning
Executing
Outcomes
Lessons Learned

## Slide 3: Project Summary and charter
EEME20002

## Slide 4: Project Summary
Who we are
Functional Description
  Task overview
    Receive command, process and return result
  Data Processor
    Find the information of peak
  Command Processor
    NNN detect
    Control TX, RX and DP

## Slide 5: Project Charter: Overall

## Slide 6: Project Charter: In Scope
DP & CP development
  From algorithm to HDL
  From simulation to synthesis & on board
  Testbench for internal small modules
Integration with provided modules
Documentation

## Slide 7: Project Charter: Out of Scope
Data generator
TX, RX
Testbenches
  Only for some internal small submodules
Power, area
Performance
  Only latency considered

## Slide 8: Project Charter: Constraints
Specifications
  100MHz at minimum
  Hardware
    Specified FPGA model
    Limited computation resources
  Compatibility with provided modules
Deadline
  16th, April

## Slide 9: Project Charter: Deliverables & Targets
Deliverables
  VHDL source code
  Technical report
  Video on group management
Targets
  Learn digital design process
  Learn group collaboration

## Slide 10: TEAM structure
EEME20002

## Slide 11: Team Structure: Overall
Data Processor Team
  Yuan Ren
  Julia Yang
Command Processor Team
  Xinrui Zhu
  Yuhao Jiang
  Xi Zhao

## Slide 12: Team Structure: Yuan Ren
Lead
  VHDL implementation
  Code review
  Report documentation
Support
  Simulation and debugging
  Meeting organisation

## Slide 13: Team Structure: Julia Yang
Lead
  Algorithm & FSM design
  Simulation and debugging
  Report Writing (DP part)
Support
  System integration
  Liaison with teaching staff

## Slide 14: Team Structure: Xinrui Zhu
Lead
  System architecture design
  Core FSM/ASM design
  System integration
  GitHub repository management
Support
  VHDL implementation
  Code review

## Slide 15: Team Structure: Yuhao Jiang
Lead
  IO controller design
  VHDL implementation
Support
  Simulation and debugging
  Progress tracking
  Report documentation (CP part)

## Slide 16: Team Structure: Xi Zhao
Lead
  Simulation and debugging
  Report Writing (CP part)
  Progress tracking
Support
  VHDL implementation
  Code review

## Slide 17: planning
EEME20002

## Slide 18: Planning: Methodology
Task division
  Work breakdown structure (WBS)
Timeline & stage deliverables
  Gantt chart
Risk control
  Risk register table

## Slide 19: Planning: Work Breakdown Structure
FPGA peak Detector
Algorithm level
Register level
Assemble
Synthesis
Submission
DP pseudocode
CP FSM
Port define
Logic design
Interconnection
CP VHDL
Design & Simulate
DP VHDL
Write code
Packaged VHDL
Link generator
FPGA Bitstream
Link Rx & Tx
Timing constraint
Report
FPGA Product
Video
Design testbench
Simulate
Test & verify

## Slide 20: Planning: Gantt Chart

## Slide 21: Planning: Risk Register
Date | Raised By | Description | Likelihood | Severity | Risk | Mitigation | Owner
28/11/2025 | Xi Zhao | Member doesn’t complete his own work before a certain deadline. | 2 | 2 | 4 | Arrange weekly meeting to check individual’s progress. | Xi Zhao
28/11/2025 | Xinrui Zhu, Yuan Ren | Simulation result doesn’t meet expectation. (e.g. can’t detect peak) | 4 | 4 | 16 | Draft the code after the algorithm is finished, pay attention to syntax errors. | Xinrui Zhu
28/11/2025 | Xinrui Zhu | FPGA timing doesn’t converge | 4 | 5 | 20 | Get familiar with FPGA workflow from lectures. | Xinrui Zhu
28/11/2025 | Yuan Ren | Team member becomes unavailable (e.g. accidentally injured) | 1 | 5 | 5 | Optimise work distribution and prepare for online collaboration. | Yuan Ren
29/11/2025 | Yuhao Jiang | FPGA board is malfunctioned or damaged | 1 | 5 | 5 | Test the functions at first time, contact university staff for replacement early. | Yuhao Jiang
01/12/2025 | Julia Yang | Inconsistent coding styles of developers leads to inconsistent module interfaces | 3 | 1 | 3 | Write ReadMe document to define essential specs, add comments next to critical code sections. | Julia Yang

## Slide 22: Planning: Limitations
Limited task information available
Limited familiarity with FPGA development process

## Slide 23: executing
EEME20002

## Slide 24: Executing: Coordination
Meetings in person
  Two three-hour sessions
  Focus on project development
Online meetings on Teams
  Learn, evaluate and prepare for next-step
GitHub: code collaboration
  GoofyAsh6795395/FPGA-peak-detector

## Slide 25: Executing: Coordination
Meetings in person
  Two three-hour sessions
  Focus on project development
Online meetings on Teams
  Learn, evaluate and prepare for next-step
GitHub: code collaboration
  GoofyAsh6795395/FPGA-peak-detector

## Slide 26: Executing: Coordination
Meetings in person
  Two three-hour sessions
  Focus on project development
Online meetings on Teams
  Learn, evaluate and prepare for next-step
GitHub: code collaboration
  GoofyAsh6795395/FPGA-peak-detector

## Slide 27: Executing: Progress Tracking
Report orally in person
Communicate on IM software
On GitHub
  Blame
  Pull requests
    Commit and File changes
In-code development log
  Rationale, outstanding tasks

## Slide 28: Executing: Progress Tracking
Report orally in person
Communicate on IM software
On GitHub
  Blame
  Pull requests
    Commit and File changes
In-code development log
  Rationale, outstanding tasks

## Slide 29: Executing: Progress Tracking
Report orally in person
Communicate on IM software
On GitHub
  Blame
  Pull requests
    Commit and File changes
In-code development log
  Rationale, outstanding tasks

## Slide 30: Executing: Technical Issues
Limited familiarity with GitHub
  Centralised management
Uneven retention of VHDL
Limited prior exposure to Vivado
  Targeted online tutorials

## Slide 31: Executing: Technical Issues
Limited familiarity with GitHub
  Centralised management
Uneven retention of VHDL
Limited prior exposure to Vivado
  Targeted online tutorials

## Slide 32: Executing: Technical Issues
Limited familiarity with GitHub
  Centralised management
Uneven retention of VHDL
Limited prior exposure to Vivado
  Targeted online tutorials

## Slide 33: Executing: Management Issues
Inaccurate time estimation
  Longer than expectation
    Algorithm & Simulation
  Short than expectation
    Assemble
Incomplete task division
  Video & Report part
Re-evaluate the task
  Based on progress and difficulty
Leave time slack for some deliverables
Update WBS, Gantt Chart

## Slide 34: outcomes
EEME20002

## Slide 35: Outcomes: FPGA Product
Functional requirements satisfied
Enhanced echo function
  Not interrupted by output stream
Higher frequency than expected
  CP: 183 MHz
  DP: 175 MHz
  Overall: 151 MHz

## Slide 36: Outcomes: Team collaboration
Clear task allocation
Regular meetings
Internal knowledge sharing

## Slide 37: LESSONS learned
EEME20002

## Slide 38: Lessons Learned: In Summary
Project management tools
  Gantt chart, WBS, risk register
Collaboration tools
  Teams, GitHub
Technical
  Digital design approach: VHDL syntax, FSM/ASM design
  Industrial toolchain
    Questa: VHDL writing, simulation
    Xilinx Vivado Design Suite: synthesis, implementation

## Slide 39: Lessons Learned: In Future
Better task interpretation before planning
A more detailed plan
  Include non-technical tasks
Improve communication efficiency
  Prepare before meeting
  Take actions after meeting